## Sheet1
wp | activity | start_date | end_date
WP1 - The knowledge map | T1.1 Building the web site | 1 | 6
WP1 - The knowledge map | T1.2 Methodology paper | 4 | 12
WP2 - Workshop and user participation | T2.1 Expert groups | 4 | 36
WP2 - Workshop and user participation | T2.2 User survey | 10 | 36
WP3 - Systematic reviews | T3.1 Systematic map | 1 | 12
WP3 - Systematic reviews | T3.2 Systematic review | 13 | 48
WP4 - Indicator documentation | T4.1 Web app | 2 | 15
WP4 - Indicator documentation | T4.1 Document and publish indicator workflows | 10 | 18
WP5 - Communication modules | T5.1 Write EA textbook | 19 | 48
WP5 - Communication modules | T5.2 Presentations | 25 | 28
WP5 - Communication modules | T5.3 Reporting standards | 13 | 36