## Sheet1
wp | activity | start_date | end_date
WP1 - The knowledge map | T1.1 Building the web site | 1 | 12
WP1 - The knowledge map | T1.2 Methodology paper | 6 | 12
WP2 - Workshop and user participation | T2.1 Populate the knowledge map | 3 | 36
WP3 - Systematic reviews | T3.1 Systematic map on the use of EC indicators | 1 | 12
WP3 - Systematic reviews | T3.2 Other systematic reviews | 12 | 48
WP4 - Indicator development | T4.1 Develop and publish indicator workflow(s) | 1 | 24
WP4 - Indicator development | T4.2 Web app for indicator documentation | 9 | 18
WP4 - Indicator development | T.4.3 eaTools | 1 | 36
WP5 - Communication modules | T5.1 Write EA textbook | 18 | 48
WP5 - Communication modules | T5.2 ECA desktop | 24 | 28
WP5 - Communication modules | T5.3 Presentations | 12 | 48